## Sheet1
Group number
3
Team members
| Name | Email
Mentor | Carlos Arocha | ca@arochaandassociates.ch
Students | Luyang Feng | LF2786@columbia. edu
| Orange | ya2538@columbia.edu
| Ruizhe Qiu | rq2194@columbia.edu
Week | Starting date | Project steps | Meetings with mentor
Week 1 | 2024-05-20 | Kickoff meeting
|  | Mentor (client) introduces goals and objectives of the project | 2024-05-23
|  | Mentor and group members get familiar | 2024-05-24
Week 2 | 2024-05-27 | Discuss project analysis method
|  | Provide proposed steps at high level | 2024-05-30
|  | Prepare Statement of work, part 1 (draft) | 2024-05-31
Week 3 | 2024-06-03 | Finalize Statement of work, part 1 | 2024-06-06
Week 4 | 2024-06-10 | Catch up with Ira and Thomas, review the SOW Part 1 draft | 2024-06-12
|  | Discussion of next steps with Carlos | 2024-06-13
Send out a professional data request email
Start working on Statement of Work part 2
Week 5 | 2024-06-17 | EDA
|  | Show the EDA work to Carlos | 2024-06-20
Build k-means clustering for home owner insurance
Start with midterm slides
Week 6 | 2024-06-24 | Continue EDA work and k-means clustering | 2024-06-26
|  | Finish midterm slides | 2024-06-27
|  | Rehearse midterm presentation | 2024-06-28
Week 7 | 2024-07-01 | Midterm Presentation | 2024-07-01
|  | Invite the supervisor and mentor for review | 2024-07-02
Week 8 | 2024-07-08 | Build models for auto, aviation hull, etc | 2024-07-10
|  | Suggest future direction for the rest of the project | 2024-07-11
Week 9 | 2024-07-15 | Start on Exposure Ratings
|  | Discuss with Carlos about exposure ratings | 2024-07-18
Week 10 | 2024-07-22 | Finalize Analysis | 2024-07-24
|  | Start on Final presentation slides | 2024-07-25
Start on Final Report
Week 11 | 2024-07-29 | Prepare final presentation | 2024-07-31
Rehearse for final presentation
Prepare Final Report
Week 12 | 2024-08-05 | Final presentation | 2024-08-06
|  | Wrap-up session | 2024-08-08
|  | Final Report | 2024-08-09